## Supply
job_name | location
meesho.supply_v2_labels_xpressbees_2023_01_01 | labels/xpressbees/2023-01-01/
meesho.supply_v2_labels_xpressbees_2023_01_02 | labels/xpressbees/2023-01-02/
meesho.supply_v2_labels_xpressbees_2023_01_03 | labels/xpressbees/2023-01-03/
meesho.supply_v2_labels_xpressbees_2023_01_04 | labels/xpressbees/2023-01-04/
meesho.supply_v2_labels_xpressbees_2023_01_05 | labels/xpressbees/2023-01-05/

## DS JOBS
S3 bucket | GCS bucket name(proposed) | Team | POC | size in GB (as of 19th oct) | size in TB (as of 19th oct) | Ready To be Migrated | Folders to be ignored | Priority | ETA | Comments | Folders to be transferred (if a folder is mentioned here, rest of the folders will not be migrated, they will be ignored)
data-science-meesho-hive | gcs-dsci-xdsci-hive-prd | Shared (ds_sliver & ofs tables) |  | 714544.91 | 697.7978 | Yes | NA | P0 | Done
meesho-supply-v2 |  |  |  | 305401.7 | 298.2438 | No |  |  |  | common bucket
data-science-meesho | gcs-dsci-xdsci-common-prd |  |  | 134701.9 | 131.5448 | Yes | NA
platform-competitive-scrap |  |  |  | 97265.11 | 94.9855 | No |  |  |  | common bucket
data-science-meesho-fy | gcs-dsci-fryou-fy-prd |  | Divay Jindal Akash Das | 84657.03 | 50 | Yes | s3://data-science-meesho-fy/generalized_feed_ranker/realtime_data s3://data-science-meesho-fy/generalized_feed_ranker/online_fs_push_v2 s3://data-science-meesho-fy/generalized_feed_ranker/gold_tables s3://data-science-meesho-fy/generalized_feed_ranker/datasets/ s3://data-science-meesho-fy/generalized_feed_ranker/features/ s3://data-science-meesho-fy/feed/ s3://data-science-meesho-fy/fy_health/ (size reduced to 33TB) | P0 | started
data-science-meesho-ads | gcs-dsci-adv-ads-prd | Ads | Parag Bhandarkar Abhiroop Kumar Abhishek Mungoli Harsh Choudhary | 79758.77 | 77.8894 | Yes | NA |  | started
data-science-meesho-search | gcs-dsci-srch-search-prd | Search | Srinivasa Rao Jami Hardik Gupta Kushagra Agarwal | 70377.32 | 68.7279 | Yes | (size is reduced to 22 TB) | P0 | started
data-science-meesho-dev-homepage | gcs-dsci-hpage-homepage-dev-prd | Homepage | Vaishnav Chandak Devashish Gupta | 65105.238 | 63.5793 | Yes | s3://data-science-meesho-dev-homepage/devashish/ s3://data-science-meesho-dev-homepage/search__user_cohorts/ s3://data-science-meesho-dev-homepage/user_clp__hp_ctr_features/ | P2 | started
data-science-meesho-image | gcs-dsci-patch-image-prd | Product Match | Srinivasa Rao Jami | 64284.92 | 62.7782 | Yes | NA (size reduced to 51.4 TB) | P0 | started
data-science-meesho-fds | gcs-dsci-fds-fds-prd | Fraud AI | Debashis Mukherjee | 60375.04 | 58.96 | Yes | NA | P0 | started
data-science-meesho-ct | gcs-dsci-explr-explore-prd | Ranking - Explore | Harshit Saxena | 58497.65 | 57.1266 | Yes | NA (size reduced to 22 TB) | P0 | started
data-science-meesho-dev-fds | gcs-dsci-fds-fds-dev-prd | Fraud AI | Debashis Mukherjee | 45300.79 | 44.2391 | Yes | s3://data-science-meesho-dev-fds/shubham/RTO/hypergraph/ s3://data-science-meesho-dev-fds/post_order_fds_training/v8/ |  | started
data-science-meesho-dev-ct | gcs-dsci-explr-explore-dev-prd | Ranking - Explore | Harshit Saxena | 40914.67 | 39.9557 | Yes | NA (size reduced to 14 TB) |  | started
data-science-meesho-dev-search | gcs-dsci-srch-search-dev-prd | Search | Kushagra Agarwal Hardik Gupta Srinivasa Rao Jami | 40578.42 | 39.6274 | Yes | s3://data-science-meesho-dev-search/embedding-retrieval/catalog_embeddings/bf16_ep4_attribute_mixed_neg_hash_seed_0/ s3://data-science-meesho-dev-search/embedding-retrieval/catalog_embeddings/que2search_v1_embeddings_qdrant_daily/ s3://data-science-meesho-dev-search/embedding-retrieval/dataset/catalog_attribute_description/ s3://data-science-meesho-dev-search/embedding-retrieval/deployment/ | P0 | started
data-science-meesho-rl | gcs-dsci-core-rl-prd | RL | Raja Mohan Reddy | 40494.68 | 39.5456 | Yes | NA | P0 | started
data-science-meesho-homepage | gcs-dsci-hpage-homepage-prd | Homepage | Vaishnav Chandak Devashish Gupta | 39120.07 | 38.2032 | Yes | s3://data-science-meesho-homepage/kaizen/ s3://data-science-meesho-homepage/scale_up/ s3://data-science-meesho-homepage/tile_ranking/ s3://data-science-meesho-homepage/user_collection__rollup_agg/ s3://data-science-meesho-homepage/user_clp__rollup_agg/ | P0 | done
data-science-meesho-notif | gcs-dsci-ugrwt-notif-prd | User Jouney | Parth Maheshwari Abhishek U Karanth | 34834.256 | 34.0178 | Yes |  | P0 | started |  | s3://data-science-meesho-notif/clp_pn/sent/, s3://data-science-meesho-notif/sp_pn/sent/, s3://data-science-meesho-notif/sp_pn/interaction_data/algo=intent_cbyv_data_gen/, s3://data-science-meesho-notif/sp_pn/gen_ai/, s3://data-science-meesho-notif/sp_pn/rt/kafka_clicks_checkpoint_new/
data-science-meesho-content | gcs-dsci-fds-content-prd | Fraud AI | Debashis Mukherjee | 33972.95 | 33.1767 | Yes |  | P0 | started
data-science-meesho-clp | gcs-dsci-ctllp-clp-prd | Ranking - CLP | Utkarsh Agrawal Akash Das | 23934.7 | 23.3737 | Yes | s3://data-science-meesho-clp/v3/clp_coll_reco/ s3://data-science-meesho-clp/v3/fyfeed_reco/ s3://data-science-meesho-clp/v3/onfs/ s3://data-science-meesho-clp/v3/feed/ s3://data-science-meesho-clp/v3/data_dump/ | P0 | started
data-science-meesho-pdp | gcs-dsci-rcmnd-pdp-prd | PDP | Raja Mohan Reddy | 23119.01 | 22.5772 | Yes | NA | P0 | started
data-science-meesho-dev-notif | gcs-dsci-ugrwt-notif-dev-prd | User Jouney | Parth Maheshwari Abhishek U Karanth | 19830.013 | 19.3652 | Yes | s3://data-science-meesho-dev-notif/fy_notif/ s3://data-science-meesho-dev-notif/sp_pn/ |  | started
datascience-fy |  |  | Divay Jindal Abhishek Mungoli | 18580.46 | 18.145 | No | Can delete this bucket
data-science-meesho-reranker | gcs-dsci-price-reranker-prd |  | Abhay Shukla Kunal Sawant Hardik Gupta | 17970.04 | 17.5489 | Yes |  |  | started
data-science-oregon | gcs-dsci-xdsci-oregon-prd | RL | Raja Mohan Reddy | 16691 | 16.2998 | No | NA | P0
data-science-meesho-return | gcs-dsci-fds-return-prd | Fraud AI | Debashis Mukherjee | 16099.87 | 15.7225 | Yes |  | P0 | started
data-science-meesho-dev-content | gcs-dsci-fds-content-dev-prd | Fraud AI | Debashis Mukherjee | 15928.753 | 15.5554 | Yes |  | P0 | started
data-science-meesho-core | gcs-dsci-core-core-prd | Quality | Aravind J Mukul Ranjan | 15123.55 | 14.7691 | Yes | s3://data-science-meesho-core/quality/retention_model/personalized_retention_model/train_data/ | P0 | started
data-science-meesho-dev-reranker | gcs-dsci-price-reranker-dev-prd |  | Abhay Shukla Kunal Sawant Hardik Gupta | 14137.92 | 13.8066 | Yes | s3://data-science-meesho-dev-reranker/soham/ s3://data-science-meesho-dev-reranker/arijit/ s3://data-science-meesho-dev-reranker/backtesting/ s3://data-science-meesho-dev-reranker/v0/ s3://data-science-meesho-dev-reranker/v2/ s3://data-science-meesho-dev-reranker/v3_table_unnest/ s3://data-science-meesho-dev-reranker/v3/ |  | started
data-science-meesho-query | gcs-dsci-srch-query-prd | Fraud AI | Debashis Mukherjee | 9851.16 | 9.6203 | Yes |  | P0 | started
data-science-meesho-dev-ads | gcs-dsci-adv-ads-dev-prd | Ads | Parag Bhandarkar Abhiroop Kumar | 9173.23 | 8.9582 | Yes | s3://data-science-meesho-dev-ads/abhiroop/ s3://data-science-meesho-dev-ads/Development/ |  | started
data-science-meesho-dev-supply | gcs-dsci-xsupl-supply-dev-prd | Supply Growth | Srinivasa Rao Jami | 7802.55 | 7.6197 | Yes |  |  | started
data-science-meesho-dev-fy | gcs-dsci-fryou-fy-dev-prd |  | Divay Jindal | 5938.97 | 5.7998 | Yes | generalized_feed_ranker/ akash/ |  | started
datascience-clp-collection | gcs-dsci-ctllp-clp-collection-prd | Ranking - CLP | Mukul Ranjan Jaya Shankar Kommuru | 3923.97 | 3.832 | Yes |  | P0 | started
data-science-meesho-dev-rl |  | RL | Raja Mohan Reddy | 2646.55 | 2.5845 | No | delete this bucket
data-science-meesho-dev-image | gcs-dsci-patch-image-dev-prd | Product Match | Srinivasa Rao Jami | 2166.7 | 2.1159 | Yes |  | P2 | done
data-science-meesho-hbase-snapshot | gcs-dsci-xdsci-hbase-snapshot-prd | Data platform |  | 1331 | 1.2998 | Yes |  |  | started
data-science-meesho-artifact | gcs-dsci-xdsci-artifact-prd |  |  | 1213.22 | 1.1848 | Yes |  | P0 | started
data-science-meesho-dev-pdp |  | PDP | Raja Mohan Reddy | 1178.85 | 1.1512 | No | delete this bucket
data-science-meesho-mlp | gcs-dsci-mlp-mlp-prd | ml-platform | Adarsha Das Dhaval Parmar Aditya Kumar Garg Jigar Dave | 837.7 | 0.81807 | Yes |  | P0 | done
data-science-meesho-dev-compliance |  | Supply Growth | Srinivasa Rao Jami | 759.19 | 0.7414 | Yes
data-science-meesho-dev-query | gcs-dsci-srch-query-dev-prd | Fraud AI | Debashis Mukherjee | 726.198 | 0.70918 | Yes |  |  | started
data-science-meesho-dev-core | gcs-dsci-core-core-dev-prd | Quality | Aravind J Mukul Ranjan | 691.189 | 0.67499 | Yes |  |  | done
data-science-meesho-supply | gcs-dsci-xsupl-supply-prd | Supply Growth | Srinivasa Rao Jami | 280.45 | 0.27388 | Yes |  | P0 | done
data-science-meesho-dev-clp | gcs-dsci-ctllp-clp-dev-prd | Ranking - CLP | Utkarsh Agrawal Akash Das | 0 | 0 | Yes |  |  | done
data-science-meesho-dev-return | gcs-dsci-fds-return-dev-prd | Fraud AI | Debashis Mukherjee | 155.597 | 0.15195 | Yes |  |  | done
meesho-databricks-billable-logs-delivery |  |  |  | 36.506 | 0.03565 | Yes
data-science-meesho-dev-ug |  |  |  | 0.23729 | 0.00023173 | No | delete this bucket
data-science-meesho-ug |  |  |  | 0.2372 | 0.00023164 | No | delete this bucket
ct-qct-v2-ds-feed | gcs-dsci-ctlng-qct_v2_feed-prd |  |  | 0.121 | 0.00011816 | Yes |  |  | done
data-science-meesho-model-repository | gcs-dsci-mlp-model_repository-prd |  |  | 0.0828 | 8.0859e-05 | Yes |  |  | done
datascience-dev-airflow |  | these will be deleted post the DBC migration |  | 0.000135 | 1.3184e-07 | No
data-science-airflow-2 |  | these will be deleted post the DBC migration |  |  | 0 | No
data-science-airflow-prod |  | these will be deleted post the DBC migration |  |  | 0 | No
data-science-airflow-prod-v2 |  | these will be deleted post the DBC migration |  |  | 0 | No
data-science-meesho-dev |  |  | This bucket is deleted |  | 0 | No
data-science-meesho-gcp-poc |  |  |  | 0 | 0
meesho-p-ads